## ACTION_QUEUE
Priority | Severity | PO Number | PO Line | Vendor | Vendor Contact | Beacon Part Number | Vendor Part Number | Description | Issue Codes | Suggested Action | Qty Ordered | Qty Confirmed | Qty Variance | PO Unit Price | PO Currency | Confirmation Unit Price | Confirmation Currency | FX Rate | Normalized Confirmation Price | Price Difference | Price Difference % | Estimated Price Impact | Required Date | Commitment Type | Promise Start | Promise End | Projected Full Qty Promise | Days Late | Match Method | Match Confidence | Source Document | Source Document Number | Document Date | Document Status
1 | RED | PO-4500050001 | 2 | Apex Bar & Tube Co. | orders@apexbar.com | BAR-A286-250 |  | A286 bar stock, 0.250 dia, mill-cert | MISSING_PO_LINE | Ask Apex Bar & Tube Co. to confirm PO-4500050001 line 2, BAR-A286-250, qty 1,500, required 2026-06-10. | 1500 |  |  | 4.71 | USD | [7 empty] | 2026-06-10 | [7 empty] | apex_02.pdf | APX-552544 | 2026-05-17 | ACTIVE
2 | RED | PO-4500050007 | 1 | Apex Bar & Tube Co. | orders@apexbar.com | BAR-A286-250 | BAR-A286-250 | A286 bar stock, 0.250 dia, mill-cert | QTY_SHORT | Resolve 75-unit short confirmation on PO-4500050007 line 1 (BAR-A286-250) before release. | 1500 | 1425 | -75 | 4.71 | USD | 4.71 | USD | 1 | 4.71 | 0 | 0% | 0 | 2026-06-15 | PROMISE_DATE | 2026-06-15 | 2026-06-15 |  | 0 | EXACT_CUSTOMER_PN | 0.99 | apex_03.pdf | APX-978346 | 2026-05-15 | ACTIVE
3 | RED | PO-4500050032 | 1 | QuickShip Industrial | orders@quickship-ind.com | MISC-WAS-A25 |  | Washer, A286, 0.25 | NO_FORMAL_ACK_FOUND;INVOICE_NOT_ACK | No formal acknowledgment found for PO-4500050032 line 1. Request an order confirmation (the invoice/shipping notice is not sufficient). | 500 |  |  | 0.06 | USD | [7 empty] | 2026-05-18 | [7 empty] | quickship_03.pdf |  |  | INFORMATIONAL
4 | RED | PO-4500050032 | 2 | QuickShip Industrial | orders@quickship-ind.com | MISC-SPR-001 |  | Spring, comp, 0.250 OD | NO_FORMAL_ACK_FOUND;INVOICE_NOT_ACK | No formal acknowledgment found for PO-4500050032 line 2. Request an order confirmation (the invoice/shipping notice is not sufficient). | 1000 |  |  | 0.18 | USD | [7 empty] | 2026-05-18 | [7 empty] | quickship_03.pdf |  |  | INFORMATIONAL
5 | RED | PO-4500060619 |  | Apex Bar & Tube Co. | orders@apexbar.com |  |  | A286 bar stock, 0.250 dia, mill-cert | UNKNOWN_PO | Verify whether this acknowledgment belongs to Beacon and whether PO number PO-4500060619 is correct. |  | 1000 | [18 empty] | apex_rogue.pdf | APX-334543 | 2026-05-15 | ACTIVE
6 | RED | PO-4500050002 | 1 | Apex Bar & Tube Co. | orders@apexbar.com | BAR-CRES-250 | BAR-CRES-250 | CRES 17-4 PH bar stock, 0.250 dia | PRICE_HIGH | Confirm acceptance of $0.0902/unit increase (~2.30%) on PO-4500050002 line 1. | 1000 | 1000 | 0 | 3.92 | USD | 4.0102 | USD | 1 | 4.0102 | 0.0902 | 2.301% | 90.2 | 2026-05-21 | PROMISE_DATE | 2026-05-21 | 2026-05-21 | 2026-05-21 | 0 | EXACT_CUSTOMER_PN | 0.99 | apex_05.pdf | APX-389235 | 2026-05-17 | ACTIVE
7 | RED | PO-4500050022 | 1 | Continental Quality Heat Treat | info@continentalqht.com | HT-PRECIP |  | Precipitation heat treat A286, per lb | PRICE_NOT_STATED;PROMISE_LATE | Ask Continental Quality Heat Treat whether required date 2026-05-21 can be recovered; current promise is 21 days late. | 500 | 500 | 0 | 2.4 | USD | [7 empty] | 2026-05-21 | PROMISE_DATE | 2026-06-11 | 2026-06-11 | 2026-06-11 | 21 | SINGLE_REMAINING_LINE | 0.6 | continental_01.pdf | CQH-41200 | 2026-05-14 | ACTIVE
8 | RED | PO-4500050012 | 1 | Heritage Cold Heading | sales@heritagecoldheading.com | CHB-9472-4 | APH-441-OS | Cold-headed blank for HX-9472-4 | PROMISE_LATE | Ask Heritage Cold Heading whether required date 2026-06-04 can be recovered; current promise is 14 days late. | 15000 | 15000 | 0 | 0.86 | USD | 0.86 | USD | 1 | 0.86 | 0 | 0% | 0 | 2026-06-04 | PROMISE_DATE | 2026-06-18 | 2026-06-18 | 2026-06-18 | 14 | RULE_BASED | 0.8 | heritage_06.pdf | HCH-74805 | 2026-05-11 | ACTIVE
9 | RED | PO-4500050016 | 1 | Liberty Surface Finishing | service@libertysurface.com | PLAT-PASV |  | Passivation per AMS 2700, per piece | PRICE_NOT_STATED;PROMISE_LATE | Ask Liberty Surface Finishing whether required date 2026-05-17 can be recovered; current promise is 7 days late. | 2500 | 2500 | 0 | 0.08 | USD | [7 empty] | 2026-05-17 | PROMISE_DATE | 2026-05-17 | 2026-05-24 | 2026-05-24 | 7 | SINGLE_REMAINING_LINE | 0.55 | liberty_01.pdf | LIB-PO-8573 | 2026-05-16 | ACTIVE
10 | RED | PO-4500050019 | 1 | Liberty Surface Finishing | service@libertysurface.com | PLAT-PASV |  | Passivation per AMS 2700, per piece | PROMISE_MISSING | Request committed quantity and promise date for PO-4500050019 line 1 (PLAT-PASV). | 25000 |  |  | 0.08 | USD | [7 empty] | 2026-05-24 | [7 empty] | liberty_03.pdf | LIB-PO-9821 | 2026-05-11 | ACTIVE
11 | YELLOW | PO-4500050027 | 1 | Ostmark Werkzeug GmbH | vertrieb@ostmark-wzg.de | TOOL-DIE-9472 | TOOL-DIE-9472 | Heading die set, 9472 profile | PROMISE_WINDOW_STRADDLES_REQUIRED | Delivery window for PO-4500050027 line 1 straddles required date 2026-05-15. Ask Ostmark Werkzeug GmbH to commit a date on or before 2026-05-15. | 25 | 25 | 0 | 1240 | USD | 1140.8 | EUR | 1.0902 | 1243.7002 | 3.7002 | 0.2984% | 92.5 | 2026-05-15 | DELIVERY_WINDOW | 2026-05-11 | 2026-05-31 | 2026-05-31 |  | EXACT_VENDOR_PN_TO_BEACON_PN | 0.9 | ostmark_01.pdf | OST-220844 | 2026-05-01 | ACTIVE
12 | YELLOW | PO-4500050027 | 2 | Ostmark Werkzeug GmbH | vertrieb@ostmark-wzg.de | TOOL-INS-CAR | OST-CAR-A-100 | Carbide threading insert, A-series | PROMISE_WINDOW_STRADDLES_REQUIRED | Delivery window for PO-4500050027 line 2 straddles required date 2026-05-15. Ask Ostmark Werkzeug GmbH to commit a date on or before 2026-05-15. | 50 | 50 | 0 | 18.2 | USD | 16.744 | EUR | 1.0902 | 18.2543 | 0.054309 | 0.2984% | 2.72 | 2026-05-15 | DELIVERY_WINDOW | 2026-05-11 | 2026-05-31 | 2026-05-31 |  | RULE_BASED | 0.8 | ostmark_01.pdf | OST-220844 | 2026-05-01 | ACTIVE
13 | YELLOW | PO-4500050030 | 1 | QuickShip Industrial | orders@quickship-ind.com | MISC-SPR-001 | MISC-SPR-001 | Spring, comp, 0.250 OD | DOCUMENT_REVISION;DOCUMENT_SUPERSEDED;DATE_SEMANTICS_WARNING | QuickShip Industrial stated a ship date (not a Beacon receipt/promise date) on PO-4500050030. Confirm whether the ship date will still meet the required date at Beacon. | 500 | 500 | 0 | 0.18 | USD | 0.18 | USD | 1 | 0.18 | 0 | 0% | 0 | 2026-05-21 | SHIP_DATE | 2026-05-21 | 2026-05-21 | 2026-05-21 | 0 | EXACT_CUSTOMER_PN | 0.99 | quickship_02.pdf |  | 2026-05-11 | ACTIVE
14 | YELLOW | PO-4500050031 | 1 | QuickShip Industrial | orders@quickship-ind.com | MISC-WAS-A25 | MISC-WAS-A25 | Washer, A286, 0.25 | DATE_SEMANTICS_WARNING | QuickShip Industrial stated a ship date (not a Beacon receipt/promise date) on PO-4500050031. Confirm whether the ship date will still meet the required date at Beacon. | 500 | 500 | 0 | 0.06 | USD | 0.06 | USD | 1 | 0.06 | 0 | 0% | 0 | 2026-05-15 | SHIP_DATE | 2026-05-15 | 2026-05-15 | 2026-05-15 | 0 | EXACT_CUSTOMER_PN | 0.99 | quickship_04.pdf |  | 2026-05-10 | ACTIVE

## ALL_PO_LINES
Severity | PO Number | PO Line | Vendor | Vendor Contact | Beacon Part Number | Vendor Part Number | Description | Issue Codes | Suggested Action | Qty Ordered | Qty Confirmed | Qty Variance | PO Unit Price | PO Currency | Confirmation Unit Price | Confirmation Currency | FX Rate | Normalized Confirmation Price | Price Difference | Price Difference % | Estimated Price Impact | Required Date | Commitment Type | Promise Start | Promise End | Projected Full Qty Promise | Days Late | Match Method | Match Confidence | Source Document | Source Document Number | Document Date | Document Status
RED | PO-4500050001 | 2 | Apex Bar & Tube Co. | orders@apexbar.com | BAR-A286-250 |  | A286 bar stock, 0.250 dia, mill-cert | MISSING_PO_LINE | Ask Apex Bar & Tube Co. to confirm PO-4500050001 line 2, BAR-A286-250, qty 1,500, required 2026-06-10. | 1500 |  |  | 4.71 | USD | [7 empty] | 2026-06-10 | [7 empty] | apex_02.pdf | APX-552544 | 2026-05-17 | ACTIVE
RED | PO-4500050007 | 1 | Apex Bar & Tube Co. | orders@apexbar.com | BAR-A286-250 | BAR-A286-250 | A286 bar stock, 0.250 dia, mill-cert | QTY_SHORT | Resolve 75-unit short confirmation on PO-4500050007 line 1 (BAR-A286-250) before release. | 1500 | 1425 | -75 | 4.71 | USD | 4.71 | USD | 1 | 4.71 | 0 | 0% | 0 | 2026-06-15 | PROMISE_DATE | 2026-06-15 | 2026-06-15 |  | 0 | EXACT_CUSTOMER_PN | 0.99 | apex_03.pdf | APX-978346 | 2026-05-15 | ACTIVE
RED | PO-4500050032 | 1 | QuickShip Industrial | orders@quickship-ind.com | MISC-WAS-A25 |  | Washer, A286, 0.25 | NO_FORMAL_ACK_FOUND;INVOICE_NOT_ACK | No formal acknowledgment found for PO-4500050032 line 1. Request an order confirmation (the invoice/shipping notice is not sufficient). | 500 |  |  | 0.06 | USD | [7 empty] | 2026-05-18 | [7 empty] | quickship_03.pdf |  |  | INFORMATIONAL
RED | PO-4500050032 | 2 | QuickShip Industrial | orders@quickship-ind.com | MISC-SPR-001 |  | Spring, comp, 0.250 OD | NO_FORMAL_ACK_FOUND;INVOICE_NOT_ACK | No formal acknowledgment found for PO-4500050032 line 2. Request an order confirmation (the invoice/shipping notice is not sufficient). | 1000 |  |  | 0.18 | USD | [7 empty] | 2026-05-18 | [7 empty] | quickship_03.pdf |  |  | INFORMATIONAL
RED | PO-4500060619 |  | Apex Bar & Tube Co. | orders@apexbar.com |  |  | A286 bar stock, 0.250 dia, mill-cert | UNKNOWN_PO | Verify whether this acknowledgment belongs to Beacon and whether PO number PO-4500060619 is correct. |  | 1000 | [18 empty] | apex_rogue.pdf | APX-334543 | 2026-05-15 | ACTIVE
RED | PO-4500050002 | 1 | Apex Bar & Tube Co. | orders@apexbar.com | BAR-CRES-250 | BAR-CRES-250 | CRES 17-4 PH bar stock, 0.250 dia | PRICE_HIGH | Confirm acceptance of $0.0902/unit increase (~2.30%) on PO-4500050002 line 1. | 1000 | 1000 | 0 | 3.92 | USD | 4.0102 | USD | 1 | 4.0102 | 0.0902 | 2.301% | 90.2 | 2026-05-21 | PROMISE_DATE | 2026-05-21 | 2026-05-21 | 2026-05-21 | 0 | EXACT_CUSTOMER_PN | 0.99 | apex_05.pdf | APX-389235 | 2026-05-17 | ACTIVE
RED | PO-4500050022 | 1 | Continental Quality Heat Treat | info@continentalqht.com | HT-PRECIP |  | Precipitation heat treat A286, per lb | PRICE_NOT_STATED;PROMISE_LATE | Ask Continental Quality Heat Treat whether required date 2026-05-21 can be recovered; current promise is 21 days late. | 500 | 500 | 0 | 2.4 | USD | [7 empty] | 2026-05-21 | PROMISE_DATE | 2026-06-11 | 2026-06-11 | 2026-06-11 | 21 | SINGLE_REMAINING_LINE | 0.6 | continental_01.pdf | CQH-41200 | 2026-05-14 | ACTIVE
RED | PO-4500050012 | 1 | Heritage Cold Heading | sales@heritagecoldheading.com | CHB-9472-4 | APH-441-OS | Cold-headed blank for HX-9472-4 | PROMISE_LATE | Ask Heritage Cold Heading whether required date 2026-06-04 can be recovered; current promise is 14 days late. | 15000 | 15000 | 0 | 0.86 | USD | 0.86 | USD | 1 | 0.86 | 0 | 0% | 0 | 2026-06-04 | PROMISE_DATE | 2026-06-18 | 2026-06-18 | 2026-06-18 | 14 | RULE_BASED | 0.8 | heritage_06.pdf | HCH-74805 | 2026-05-11 | ACTIVE
RED | PO-4500050016 | 1 | Liberty Surface Finishing | service@libertysurface.com | PLAT-PASV |  | Passivation per AMS 2700, per piece | PRICE_NOT_STATED;PROMISE_LATE | Ask Liberty Surface Finishing whether required date 2026-05-17 can be recovered; current promise is 7 days late. | 2500 | 2500 | 0 | 0.08 | USD | [7 empty] | 2026-05-17 | PROMISE_DATE | 2026-05-17 | 2026-05-24 | 2026-05-24 | 7 | SINGLE_REMAINING_LINE | 0.55 | liberty_01.pdf | LIB-PO-8573 | 2026-05-16 | ACTIVE
RED | PO-4500050019 | 1 | Liberty Surface Finishing | service@libertysurface.com | PLAT-PASV |  | Passivation per AMS 2700, per piece | PROMISE_MISSING | Request committed quantity and promise date for PO-4500050019 line 1 (PLAT-PASV). | 25000 |  |  | 0.08 | USD | [7 empty] | 2026-05-24 | [7 empty] | liberty_03.pdf | LIB-PO-9821 | 2026-05-11 | ACTIVE
YELLOW | PO-4500050027 | 1 | Ostmark Werkzeug GmbH | vertrieb@ostmark-wzg.de | TOOL-DIE-9472 | TOOL-DIE-9472 | Heading die set, 9472 profile | PROMISE_WINDOW_STRADDLES_REQUIRED | Delivery window for PO-4500050027 line 1 straddles required date 2026-05-15. Ask Ostmark Werkzeug GmbH to commit a date on or before 2026-05-15. | 25 | 25 | 0 | 1240 | USD | 1140.8 | EUR | 1.0902 | 1243.7002 | 3.7002 | 0.2984% | 92.5 | 2026-05-15 | DELIVERY_WINDOW | 2026-05-11 | 2026-05-31 | 2026-05-31 |  | EXACT_VENDOR_PN_TO_BEACON_PN | 0.9 | ostmark_01.pdf | OST-220844 | 2026-05-01 | ACTIVE
YELLOW | PO-4500050027 | 2 | Ostmark Werkzeug GmbH | vertrieb@ostmark-wzg.de | TOOL-INS-CAR | OST-CAR-A-100 | Carbide threading insert, A-series | PROMISE_WINDOW_STRADDLES_REQUIRED | Delivery window for PO-4500050027 line 2 straddles required date 2026-05-15. Ask Ostmark Werkzeug GmbH to commit a date on or before 2026-05-15. | 50 | 50 | 0 | 18.2 | USD | 16.744 | EUR | 1.0902 | 18.2543 | 0.054309 | 0.2984% | 2.72 | 2026-05-15 | DELIVERY_WINDOW | 2026-05-11 | 2026-05-31 | 2026-05-31 |  | RULE_BASED | 0.8 | ostmark_01.pdf | OST-220844 | 2026-05-01 | ACTIVE
YELLOW | PO-4500050030 | 1 | QuickShip Industrial | orders@quickship-ind.com | MISC-SPR-001 | MISC-SPR-001 | Spring, comp, 0.250 OD | DOCUMENT_REVISION;DOCUMENT_SUPERSEDED;DATE_SEMANTICS_WARNING | QuickShip Industrial stated a ship date (not a Beacon receipt/promise date) on PO-4500050030. Confirm whether the ship date will still meet the required date at Beacon. | 500 | 500 | 0 | 0.18 | USD | 0.18 | USD | 1 | 0.18 | 0 | 0% | 0 | 2026-05-21 | SHIP_DATE | 2026-05-21 | 2026-05-21 | 2026-05-21 | 0 | EXACT_CUSTOMER_PN | 0.99 | quickship_02.pdf |  | 2026-05-11 | ACTIVE
YELLOW | PO-4500050031 | 1 | QuickShip Industrial | orders@quickship-ind.com | MISC-WAS-A25 | MISC-WAS-A25 | Washer, A286, 0.25 | DATE_SEMANTICS_WARNING | QuickShip Industrial stated a ship date (not a Beacon receipt/promise date) on PO-4500050031. Confirm whether the ship date will still meet the required date at Beacon. | 500 | 500 | 0 | 0.06 | USD | 0.06 | USD | 1 | 0.06 | 0 | 0% | 0 | 2026-05-15 | SHIP_DATE | 2026-05-15 | 2026-05-15 | 2026-05-15 | 0 | EXACT_CUSTOMER_PN | 0.99 | quickship_04.pdf |  | 2026-05-10 | ACTIVE
INFO | PO-4500050017 | 1 | Liberty Surface Finishing | service@libertysurface.com | PLAT-CAD |  | Cadmium plating per QQ-P-416, per piece | PRICE_NOT_STATED | Confirmation for PO-4500050017 line 1 omits price; do not treat this as price acceptance. | 2500 | 2500 | 0 | 0.11 | USD | [7 empty] | 2026-05-28 | PROMISE_DATE | 2026-05-28 | 2026-05-28 | 2026-05-28 | 0 | SINGLE_REMAINING_LINE | 0.55 | liberty_04.pdf | LIB-PO-9182 | 2026-05-15 | ACTIVE
INFO | PO-4500050018 | 1 | Liberty Surface Finishing | service@libertysurface.com | PLAT-CAD |  | Cadmium plating per QQ-P-416, per piece | PRICE_NOT_STATED | Confirmation for PO-4500050018 line 1 omits price; do not treat this as price acceptance. | 2500 | 2500 | 0 | 0.11 | USD | [7 empty] | 2026-05-19 | PROMISE_DATE | 2026-05-19 | 2026-05-19 | 2026-05-19 | 0 | SINGLE_REMAINING_LINE | 0.55 | liberty_06.pdf | LIB-PO-9157 | 2026-05-14 | ACTIVE
INFO | PO-4500050020 | 1 | Liberty Surface Finishing | service@libertysurface.com | PLAT-CAD |  | Cadmium plating per QQ-P-416, per piece | PRICE_NOT_STATED | Confirmation for PO-4500050020 line 1 omits price; do not treat this as price acceptance. | 10000 | 10000 | 0 | 0.11 | USD | [7 empty] | 2026-05-17 | PROMISE_DATE | 2026-05-17 | 2026-05-17 | 2026-05-17 | 0 | SINGLE_REMAINING_LINE | 0.55 | liberty_07.pdf | LIB-PO-9815 | 2026-05-14 | ACTIVE
INFO | PO-4500050021 | 1 | Liberty Surface Finishing | service@libertysurface.com | PLAT-PASV |  | Passivation per AMS 2700, per piece | PRICE_NOT_STATED | Confirmation for PO-4500050021 line 1 omits price; do not treat this as price acceptance. | 2500 | 2500 | 0 | 0.08 | USD | [7 empty] | 2026-05-13 | PROMISE_DATE | 2026-05-13 | 2026-05-13 | 2026-05-13 | 0 | SINGLE_REMAINING_LINE | 0.55 | liberty_05.pdf | LIB-PO-9126 | 2026-05-10 | ACTIVE
INFO | PO-4500050023 | 1 | Continental Quality Heat Treat | info@continentalqht.com | HT-PRECIP |  | Precipitation heat treat A286, per lb | PRICE_NOT_STATED | Confirmation for PO-4500050023 line 1 omits price; do not treat this as price acceptance. | 750 | 750 | 0 | 2.4 | USD | [7 empty] | 2026-05-23 | PROMISE_DATE | 2026-05-23 | 2026-05-23 | 2026-05-23 | 0 | SINGLE_REMAINING_LINE | 0.6 | continental_04.pdf | CQH-42657 | 2026-05-12 | ACTIVE
INFO | PO-4500050024 | 1 | Continental Quality Heat Treat | info@continentalqht.com | HT-SOLN |  | Solution treat + age, per lb | PRICE_NOT_STATED | Confirmation for PO-4500050024 line 1 omits price; do not treat this as price acceptance. | 350 | 350 | 0 | 3.1 | USD | [7 empty] | 2026-05-09 | PROMISE_DATE | 2026-05-09 | 2026-05-09 | 2026-05-09 | 0 | SINGLE_REMAINING_LINE | 0.6 | continental_03.pdf | CQH-40704 | 2026-05-16 | ACTIVE
INFO | PO-4500050025 | 1 | Continental Quality Heat Treat | info@continentalqht.com | HT-SOLN |  | Solution treat + age, per lb | PRICE_NOT_STATED | Confirmation for PO-4500050025 line 1 omits price; do not treat this as price acceptance. | 350 | 350 | 0 | 3.1 | USD | [7 empty] | 2026-05-07 | PROMISE_DATE | 2026-05-07 | 2026-05-07 | 2026-05-07 | 0 | SINGLE_REMAINING_LINE | 0.6 | continental_02.pdf | CQH-48302 | 2026-05-14 | ACTIVE
GREEN | PO-4500050029 | 1 | Ostmark Werkzeug GmbH | vertrieb@ostmark-wzg.de | TOOL-DIE-9472 | TOOL-DIE-9472 | Heading die set, 9472 profile |  | Review PO-4500050029 line 1 with Ostmark Werkzeug GmbH. | 5 | 5 | 0 | 1240 | USD | 1140.8 | EUR | 1.0902 | 1243.7002 | 3.7002 | 0.2984% | 18.5 | 2026-06-08 | PROMISE_DATE | 2026-06-08 | 2026-06-08 | 2026-06-08 | 0 | EXACT_VENDOR_PN_TO_BEACON_PN | 0.9 | ostmark_02.pdf | OST-224427 | 2026-05-07 | ACTIVE
GREEN | PO-4500050029 | 2 | Ostmark Werkzeug GmbH | vertrieb@ostmark-wzg.de | TOOL-INS-CAR | OST-CAR-A-100 | Carbide threading insert, A-series |  | Review PO-4500050029 line 2 with Ostmark Werkzeug GmbH. | 250 | 250 | 0 | 18.2 | USD | 16.744 | EUR | 1.0902 | 18.2543 | 0.054309 | 0.2984% | 13.58 | 2026-06-08 | PROMISE_DATE | 2026-06-08 | 2026-06-08 | 2026-06-08 | 0 | RULE_BASED | 0.8 | ostmark_02.pdf | OST-224427 | 2026-05-07 | ACTIVE
GREEN | PO-4500050028 | 1 | Ostmark Werkzeug GmbH | vertrieb@ostmark-wzg.de | TOOL-DIE-9472 | TOOL-DIE-9472 | Heading die set, 9472 profile |  | Review PO-4500050028 line 1 with Ostmark Werkzeug GmbH. | 5 | 5 | 0 | 1240 | USD | 1140.8 | EUR | 1.0874 | 1240.5059 | 0.50592 | 0.0408% | 2.53 | 2026-06-13 | PROMISE_DATE | 2026-06-13 | 2026-06-13 | 2026-06-13 | 0 | EXACT_VENDOR_PN_TO_BEACON_PN | 0.9 | ostmark_04.pdf | OST-226935 | 2026-04-30 | ACTIVE
GREEN | PO-4500050026 | 1 | Ostmark Werkzeug GmbH | vertrieb@ostmark-wzg.de | TOOL-INS-CAR | OST-CAR-A-100 | Carbide threading insert, A-series |  | Review PO-4500050026 line 1 with Ostmark Werkzeug GmbH. | 250 | 250 | 0 | 18.2 | USD | 16.744 | EUR | 1.0874 | 18.2074 | 0.007426 | 0.0408% | 1.86 | 2026-07-02 | PROMISE_DATE | 2026-07-02 | 2026-07-02 | 2026-07-02 | 0 | RULE_BASED | 0.8 | ostmark_03.pdf | OST-229377 | 2026-04-30 | ACTIVE
GREEN | PO-4500050001 | 1 | Apex Bar & Tube Co. | orders@apexbar.com | BAR-A286-375 | BAR-A286-375 | A286 bar stock, 0.375 dia, mill-cert |  | Review PO-4500050001 line 1 with Apex Bar & Tube Co.. | 2500 | 2500 | 0 | 7.84 | USD | 7.84 | USD | 1 | 7.84 | 0 | 0% | 0 | 2026-06-10 | PROMISE_DATE | 2026-06-10 | 2026-06-10 | 2026-06-10 | 0 | EXACT_CUSTOMER_PN | 0.99 | apex_02.pdf | APX-552544 | 2026-05-17 | ACTIVE
GREEN | PO-4500050003 | 1 | Apex Bar & Tube Co. | orders@apexbar.com | BAR-CRES-250 | BAR-CRES-250 | CRES 17-4 PH bar stock, 0.250 dia |  | Review PO-4500050003 line 1 with Apex Bar & Tube Co.. | 1500 | 1500 | 0 | 3.92 | USD | 3.92 | USD | 1 | 3.92 | 0 | 0% | 0 | 2026-05-30 | PROMISE_DATE | 2026-05-30 | 2026-05-30 | 2026-05-30 | 0 | EXACT_CUSTOMER_PN | 0.99 | apex_07.pdf | APX-932684 | 2026-05-16 | ACTIVE
GREEN | PO-4500050004 | 1 | Apex Bar & Tube Co. | orders@apexbar.com | BAR-A286-250 | BAR-A286-250 | A286 bar stock, 0.250 dia, mill-cert |  | Review PO-4500050004 line 1 with Apex Bar & Tube Co.. | 200 | 200 | 0 | 4.71 | USD | 4.71 | USD | 1 | 4.71 | 0 | 0% | 0 | 2026-05-21 | PROMISE_DATE | 2026-05-21 | 2026-05-21 | 2026-05-21 | 0 | EXACT_CUSTOMER_PN | 0.99 | apex_01.pdf | APX-408970 | 2026-05-06 | ACTIVE
GREEN | PO-4500050005 | 1 | Apex Bar & Tube Co. | orders@apexbar.com | BAR-A286-250 | BAR-A286-250 | A286 bar stock, 0.250 dia, mill-cert |  | Review PO-4500050005 line 1 with Apex Bar & Tube Co.. | 1500 | 1500 | 0 | 4.71 | USD | 4.71 | USD | 1 | 4.71 | 0 | 0% | 0 | 2026-06-09 | PROMISE_DATE | 2026-06-09 | 2026-06-09 | 2026-06-09 | 0 | EXACT_CUSTOMER_PN | 0.99 | apex_08.pdf | APX-945201 | 2026-05-05 | ACTIVE
GREEN | PO-4500050006 | 1 | Apex Bar & Tube Co. | orders@apexbar.com | BAR-A286-375 | BAR-A286-375 | A286 bar stock, 0.375 dia, mill-cert |  | Review PO-4500050006 line 1 with Apex Bar & Tube Co.. | 5000 | 5000 | 0 | 7.84 | USD | 7.84 | USD | 1 | 7.84 | 0 | 0% | 0 | 2026-06-14 | PROMISE_DATE | 2026-06-14 | 2026-06-14 | 2026-06-14 | 0 | EXACT_CUSTOMER_PN | 0.99 | apex_06.pdf | APX-253836 | 2026-05-04 | ACTIVE
GREEN | PO-4500050008 | 1 | Apex Bar & Tube Co. | orders@apexbar.com | BAR-A286-250 | BAR-A286-250 | A286 bar stock, 0.250 dia, mill-cert |  | Review PO-4500050008 line 1 with Apex Bar & Tube Co.. | 1000 | 1000 | 0 | 4.71 | USD | 4.71 | USD | 1 | 4.71 | 0 | 0% | 0 | 2026-05-28 | PROMISE_DATE | 2026-05-28 | 2026-05-28 | 2026-05-28 | 0 | EXACT_CUSTOMER_PN | 0.99 | apex_04.pdf | APX-737955 | 2026-05-07 | ACTIVE
GREEN | PO-4500050008 | 2 | Apex Bar & Tube Co. | orders@apexbar.com | BAR-TI64-188 | BAR-TI64-188 | Ti-6Al-4V bar stock, 0.188 dia |  | Review PO-4500050008 line 2 with Apex Bar & Tube Co.. | 1000 | 1000 | 0 | 22.5 | USD | 22.5 | USD | 1 | 22.5 | 0 | 0% | 0 | 2026-05-28 | PROMISE_DATE | 2026-05-28 | 2026-05-28 | 2026-05-28 | 0 | EXACT_CUSTOMER_PN | 0.99 | apex_04.pdf | APX-737955 | 2026-05-07 | ACTIVE
GREEN | PO-4500050009 | 1 | Heritage Cold Heading | sales@heritagecoldheading.com | CHB-9472-3 | APH-441 | Cold-headed blank for HX-9472-3 |  | Review PO-4500050009 line 1 with Heritage Cold Heading. | 50000 | 50000 | 0 | 0.84 | USD | 0.84 | USD | 1 | 0.84 | 0 | 0% | 0 | 2026-06-08 | PROMISE_DATE | 2026-06-08 | 2026-06-08 | 2026-06-08 | 0 | APPROVED_VENDOR_CROSSWALK | 0.92 | heritage_01.pdf | HCH-75140 | 2026-05-03 | ACTIVE
GREEN | PO-4500050010 | 1 | Heritage Cold Heading | sales@heritagecoldheading.com | CHB-7715 | CHB-7715 | Cold-headed blank for CSK-7715 |  | Review PO-4500050010 line 1 with Heritage Cold Heading. | 25000 | 25000 | 0 | 0.62 | USD | 0.62 | USD | 1 | 0.62 | 0 | 0% | 0 | 2026-06-23 | PROMISE_DATE | 2026-06-23 | 2026-06-23 | 2026-06-23 | 0 | EXACT_VENDOR_PN_TO_BEACON_PN | 0.9 | heritage_04.pdf | HCH-77215 | 2026-05-12 | ACTIVE
GREEN | PO-4500050011 | 1 | Heritage Cold Heading | sales@heritagecoldheading.com | CHB-9472-3 | APH-441 | Cold-headed blank for HX-9472-3 |  | Review PO-4500050011 line 1 with Heritage Cold Heading. | 5000 | 5000 | 0 | 0.84 | USD | 0.84 | USD | 1 | 0.84 | 0 | 0% | 0 | 2026-06-04 | PROMISE_DATE | 2026-06-04 | 2026-06-04 | 2026-06-04 | 0 | APPROVED_VENDOR_CROSSWALK | 0.92 | heritage_07.pdf | HCH-72939 | 2026-05-10 | ACTIVE
GREEN | PO-4500050011 | 2 | Heritage Cold Heading | sales@heritagecoldheading.com | CHB-3301 | CHB-3301 | Cold-headed blank for NUT-3301-N |  | Review PO-4500050011 line 2 with Heritage Cold Heading. | 25000 | 25000 | 0 | 0.41 | USD | 0.41 | USD | 1 | 0.41 | 0 | 0% | 0 | 2026-06-04 | PROMISE_DATE | 2026-06-04 | 2026-06-04 | 2026-06-04 | 0 | EXACT_VENDOR_PN_TO_BEACON_PN | 0.9 | heritage_07.pdf | HCH-72939 | 2026-05-10 | ACTIVE
GREEN | PO-4500050011 | 3 | Heritage Cold Heading | sales@heritagecoldheading.com | CHB-7715 | CHB-7715 | Cold-headed blank for CSK-7715 |  | Review PO-4500050011 line 3 with Heritage Cold Heading. | 25000 | 25000 | 0 | 0.62 | USD | 0.62 | USD | 1 | 0.62 | 0 | 0% | 0 | 2026-06-04 | PROMISE_DATE | 2026-06-04 | 2026-06-04 | 2026-06-04 | 0 | EXACT_VENDOR_PN_TO_BEACON_PN | 0.9 | heritage_07.pdf | HCH-72939 | 2026-05-10 | ACTIVE
GREEN | PO-4500050013 | 1 | Heritage Cold Heading | sales@heritagecoldheading.com | CHB-7715 | CHB-7715 | Cold-headed blank for CSK-7715 |  | Review PO-4500050013 line 1 with Heritage Cold Heading. | 25000 | 25000 | 0 | 0.62 | USD | 0.62 | USD | 1 | 0.62 | 0 | 0% | 0 | 2026-05-18 | PROMISE_DATE | 2026-05-18 | 2026-05-18 | 2026-05-18 | 0 | EXACT_VENDOR_PN_TO_BEACON_PN | 0.9 | heritage_03.pdf | HCH-77346 | 2026-05-08 | ACTIVE
GREEN | PO-4500050013 | 2 | Heritage Cold Heading | sales@heritagecoldheading.com | CHB-9472-3 | APH-441 | Cold-headed blank for HX-9472-3 |  | Review PO-4500050013 line 2 with Heritage Cold Heading. | 5000 | 5000 | 0 | 0.84 | USD | 0.84 | USD | 1 | 0.84 | 0 | 0% | 0 | 2026-05-18 | PROMISE_DATE | 2026-05-18 | 2026-05-18 | 2026-05-18 | 0 | APPROVED_VENDOR_CROSSWALK | 0.92 | heritage_03.pdf | HCH-77346 | 2026-05-08 | ACTIVE
GREEN | PO-4500050014 | 1 | Heritage Cold Heading | sales@heritagecoldheading.com | CHB-9472-3 | APH-441 | Cold-headed blank for HX-9472-3 |  | Review PO-4500050014 line 1 with Heritage Cold Heading. | 25000 | 25000 | 0 | 0.84 | USD | 0.84 | USD | 1 | 0.84 | 0 | 0% | 0 | 2026-06-07 | PROMISE_DATE | 2026-06-07 | 2026-06-07 | 2026-06-07 | 0 | APPROVED_VENDOR_CROSSWALK | 0.92 | heritage_05.pdf | HCH-78781 | 2026-05-02 | ACTIVE
GREEN | PO-4500050014 | 2 | Heritage Cold Heading | sales@heritagecoldheading.com | CHB-3301 | CHB-3301 | Cold-headed blank for NUT-3301-N |  | Review PO-4500050014 line 2 with Heritage Cold Heading. | 25000 | 25000 | 0 | 0.41 | USD | 0.41 | USD | 1 | 0.41 | 0 | 0% | 0 | 2026-06-07 | PROMISE_DATE | 2026-06-07 | 2026-06-07 | 2026-06-07 | 0 | EXACT_VENDOR_PN_TO_BEACON_PN | 0.9 | heritage_05.pdf | HCH-78781 | 2026-05-02 | ACTIVE
GREEN | PO-4500050014 | 3 | Heritage Cold Heading | sales@heritagecoldheading.com | CHB-7715 | CHB-7715 | Cold-headed blank for CSK-7715 |  | Review PO-4500050014 line 3 with Heritage Cold Heading. | 10000 | 10000 | 0 | 0.62 | USD | 0.62 | USD | 1 | 0.62 | 0 | 0% | 0 | 2026-06-07 | PROMISE_DATE | 2026-06-07 | 2026-06-07 | 2026-06-07 | 0 | EXACT_VENDOR_PN_TO_BEACON_PN | 0.9 | heritage_05.pdf | HCH-78781 | 2026-05-02 | ACTIVE
GREEN | PO-4500050015 | 1 | Heritage Cold Heading | sales@heritagecoldheading.com | CHB-9472-4 | APH-441-OS | Cold-headed blank for HX-9472-4 |  | Review PO-4500050015 line 1 with Heritage Cold Heading. | 25000 | 25000 | 0 | 0.86 | USD | 0.86 | USD | 1 | 0.86 | 0 | 0% | 0 | 2026-06-17 | PROMISE_DATE | 2026-06-17 | 2026-06-17 | 2026-06-17 | 0 | RULE_BASED | 0.8 | heritage_02.pdf | HCH-75668 | 2026-05-13 | ACTIVE
GREEN | PO-4500050015 | 2 | Heritage Cold Heading | sales@heritagecoldheading.com | CHB-7715 | CHB-7715 | Cold-headed blank for CSK-7715 |  | Review PO-4500050015 line 2 with Heritage Cold Heading. | 25000 | 25000 | 0 | 0.62 | USD | 0.62 | USD | 1 | 0.62 | 0 | 0% | 0 | 2026-06-17 | PROMISE_DATE | 2026-06-17 | 2026-06-17 | 2026-06-17 | 0 | EXACT_VENDOR_PN_TO_BEACON_PN | 0.9 | heritage_02.pdf | HCH-75668 | 2026-05-13 | ACTIVE
GREEN | PO-4500050015 | 3 | Heritage Cold Heading | sales@heritagecoldheading.com | CHB-9472-3 | APH-441 | Cold-headed blank for HX-9472-3 |  | Review PO-4500050015 line 3 with Heritage Cold Heading. | 5000 | 5000 | 0 | 0.84 | USD | 0.84 | USD | 1 | 0.84 | 0 | 0% | 0 | 2026-06-17 | PROMISE_DATE | 2026-06-17 | 2026-06-17 | 2026-06-17 | 0 | APPROVED_VENDOR_CROSSWALK | 0.92 | heritage_02.pdf | HCH-75668 | 2026-05-13 | ACTIVE

## DOCUMENTS
Source File | SHA256 | Vendor (raw) | PO Number | Document Number | Document Date | Document Type | Commitment Status | Lifecycle | Revision? | Supersedes prior? | Part N | Part M | Currency | Line Count | Extraction Mode | Model | Cached? | Warnings | Notes
apex_01.pdf | a2b124191abb | Apex Bar & Tube Co. | PO-4500050004 | APX-408970 | 2026-05-06 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 1 | LOCAL_TEXT | local-parser-v1 | Y
apex_02.pdf | d41e5965ac0d | Apex Bar & Tube Co. | PO-4500050001 | APX-552544 | 2026-05-17 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 1 | LOCAL_TEXT | local-parser-v1 | Y
apex_03.pdf | 1e36a3bb8230 | Apex Bar & Tube Co. | PO-4500050007 | APX-978346 | 2026-05-15 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 1 | LOCAL_TEXT | local-parser-v1 | Y
apex_04.pdf | b109ebc6b485 | Apex Bar & Tube Co. | PO-4500050008 | APX-737955 | 2026-05-07 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 2 | LOCAL_TEXT | local-parser-v1 | Y
apex_05.pdf | 527671baf80d | Apex Bar & Tube Co. | PO-4500050002 | APX-389235 | 2026-05-17 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 1 | LOCAL_TEXT | local-parser-v1 | Y
apex_06.pdf | 78e12caee3d0 | Apex Bar & Tube Co. | PO-4500050006 | APX-253836 | 2026-05-04 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 1 | LOCAL_TEXT | local-parser-v1 | Y
apex_07.pdf | 3a93a05eccfb | Apex Bar & Tube Co. | PO-4500050003 | APX-932684 | 2026-05-16 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 1 | LOCAL_TEXT | local-parser-v1 | Y
apex_08.pdf | 498d9e57c248 | Apex Bar & Tube Co. | PO-4500050005 | APX-945201 | 2026-05-05 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 1 | LOCAL_TEXT | local-parser-v1 | Y
apex_rogue.pdf | 666ddb95cb5e | Apex Bar & Tube Co. | PO-4500060619 | APX-334543 | 2026-05-15 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 1 | LOCAL_TEXT | local-parser-v1 | Y
continental_01.pdf | 171acbfe62b4 | Continental Quality Heat Treat | PO-4500050022 | CQH-41200 | 2026-05-14 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  |  | 1 | OCR_LOCAL | local-parser-v1 | Y | Extracted via OCR; native PDF text was empty
continental_02.pdf | bccc160e1d7a | Continental Quality Heat Treat | PO-4500050025 | CQH-48302 | 2026-05-14 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  |  | 1 | OCR_LOCAL | local-parser-v1 | Y | Extracted via OCR; native PDF text was empty
continental_03.pdf | ce09a43a057d | Continental Quality Heat Treat | PO-4500050024 | CQH-40704 | 2026-05-16 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  |  | 1 | OCR_LOCAL | local-parser-v1 | Y | Extracted via OCR; native PDF text was empty
continental_04.pdf | 0335b5f9c32c | Continental Quality Heat Treat | PO-4500050023 | CQH-42657 | 2026-05-12 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  |  | 1 | OCR_LOCAL | local-parser-v1 | Y | Extracted via OCR; native PDF text was empty
heritage_01.pdf | 955c6553efee | Heritage Cold Heading | PO-4500050009 | HCH-75140 | 2026-05-03 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 1 | LOCAL_TEXT | local-parser-v1 | Y
heritage_02.pdf | 803cca7204dd | Heritage Cold Heading | PO-4500050015 | HCH-75668 | 2026-05-13 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 3 | LOCAL_TEXT | local-parser-v1 | Y
heritage_03.pdf | 5c96fdc23f2b | Heritage Cold Heading | PO-4500050013 | HCH-77346 | 2026-05-08 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 2 | LOCAL_TEXT | local-parser-v1 | Y
heritage_04.pdf | da7824243c72 | Heritage Cold Heading | PO-4500050010 | HCH-77215 | 2026-05-12 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 1 | LOCAL_TEXT | local-parser-v1 | Y
heritage_05.pdf | 0f0f0358478e | Heritage Cold Heading | PO-4500050014 | HCH-78781 | 2026-05-02 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 3 | LOCAL_TEXT | local-parser-v1 | Y
heritage_06.pdf | 33d82e21944f | Heritage Cold Heading | PO-4500050012 | HCH-74805 | 2026-05-11 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 1 | LOCAL_TEXT | local-parser-v1 | Y
heritage_07.pdf | 22e8e11993b9 | Heritage Cold Heading | PO-4500050011 | HCH-72939 | 2026-05-10 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 3 | LOCAL_TEXT | local-parser-v1 | Y
liberty_01.pdf | c4b891a575c5 | Liberty Surface Finishing | PO-4500050016 | LIB-PO-9240 | 2026-05-13 | ACKNOWLEDGEMENT | PARTIAL | ACTIVE | N | N | 1 | 2 |  | 1 | LOCAL_TEXT | local-parser-v1 | Y |  | Split acknowledgment part 1 of 2
liberty_02.pdf | 064f140583b6 | Liberty Surface Finishing | PO-4500050016 | LIB-PO-8573 | 2026-05-16 | ACKNOWLEDGEMENT | PARTIAL | ACTIVE | N | N | 2 | 2 |  | 1 | LOCAL_TEXT | local-parser-v1 | Y |  | Split acknowledgment part 2 of 2
liberty_03.pdf | df73e325ff79 | Liberty Surface Finishing | PO-4500050019 | LIB-PO-9821 | 2026-05-11 | RECEIPT_ONLY | RECEIPT_ACKNOWLEDGED_NO_SCHEDULE | ACTIVE | N | N |  |  |  | 0 | LOCAL_TEXT | local-parser-v1 | Y
liberty_04.pdf | e091bfef23ea | Liberty Surface Finishing | PO-4500050017 | LIB-PO-9182 | 2026-05-15 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  |  | 1 | LOCAL_TEXT | local-parser-v1 | Y
liberty_05.pdf | e8a55dd92b82 | Liberty Surface Finishing | PO-4500050021 | LIB-PO-9126 | 2026-05-10 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  |  | 1 | LOCAL_TEXT | local-parser-v1 | Y
liberty_06.pdf | 57987fd5631a | Liberty Surface Finishing | PO-4500050018 | LIB-PO-9157 | 2026-05-14 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  |  | 1 | LOCAL_TEXT | local-parser-v1 | Y
liberty_07.pdf | cb089f26bc54 | Liberty Surface Finishing | PO-4500050020 | LIB-PO-9815 | 2026-05-14 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  |  | 1 | LOCAL_TEXT | local-parser-v1 | Y
ostmark_01.pdf | 7824420c3184 | Ostmark Werkzeug GmbH | PO-4500050027 | OST-220844 | 2026-05-01 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | EUR | 2 | LOCAL_TEXT | local-parser-v1 | Y
ostmark_02.pdf | 7dbe09998647 | Ostmark Werkzeug GmbH | PO-4500050029 | OST-224427 | 2026-05-07 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | EUR | 2 | LOCAL_TEXT | local-parser-v1 | Y
ostmark_03.pdf | 9e089392ebf2 | Ostmark Werkzeug GmbH | PO-4500050026 | OST-229377 | 2026-04-30 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | EUR | 1 | LOCAL_TEXT | local-parser-v1 | Y
ostmark_04.pdf | af20c417f7de | Ostmark Werkzeug GmbH | PO-4500050028 | OST-226935 | 2026-04-30 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | EUR | 1 | LOCAL_TEXT | local-parser-v1 | Y
quickship_01.pdf | 450c226ef559 | QuickShip Industrial | PO-4500050030 |  | 2026-05-06 | ACKNOWLEDGEMENT | FULL | SUPERSEDED | N | N |  |  | USD | 1 | LOCAL_TEXT | local-parser-v1 | Y
quickship_02.pdf | 8c7d47657ef5 | QuickShip Industrial | PO-4500050030 |  | 2026-05-11 | REVISION | FULL | ACTIVE | Y | Y |  |  | USD | 1 | LOCAL_TEXT | local-parser-v1 | Y
quickship_03.pdf | e614ec5ee714 | QuickShip Industrial | PO-4500050032 |  | 2026-05-14 | INVOICE | UNKNOWN | INFORMATIONAL | N | N |  |  | USD | 2 | LOCAL_TEXT | local-parser-v1 | Y
quickship_04.pdf | 013b7d72a0f6 | QuickShip Industrial | PO-4500050031 |  | 2026-05-10 | ACKNOWLEDGEMENT | FULL | ACTIVE | N | N |  |  | USD | 1 | LOCAL_TEXT | local-parser-v1 | Y

## PART_MAPPING
Vendor ID | Vendor Name | Vendor PN | Beacon PN | Evidence Count | Vendor PN Total | Purity | First Seen | Last Seen | Status | Source
V002 | Heritage Cold Heading | APH-125 | CHB-3301 | 36 | 36 | 100% | 2025-09-04 | 2026-03-19 | APPROVED | historical_confirmation
V002 | Heritage Cold Heading | APH-318 | CHB-7715 | 44 | 44 | 100% | 2025-09-17 | 2026-04-03 | APPROVED | historical_confirmation
V002 | Heritage Cold Heading | APH-441 | CHB-9472-3 | 30 | 30 | 100% | 2025-09-10 | 2026-04-02 | APPROVED | historical_confirmation
V002 | Heritage Cold Heading | APH-4411 | CHB-9472-4 | 35 | 35 | 100% | 2025-09-04 | 2026-03-22 | APPROVED | historical_confirmation
V002 | Heritage Cold Heading | K-1050 | CHB-5520 | 41 | 41 | 100% | 2025-09-03 | 2026-03-31 | APPROVED | historical_confirmation
V005 | Ostmark Werkzeug GmbH | K-1050 | TOOL-PUNCH-STD | 18 | 18 | 100% | 2025-09-14 | 2026-02-27 | APPROVED | historical_confirmation
V005 | Ostmark Werkzeug GmbH | WZ-9472-DS | TOOL-DIE-9472 | 20 | 20 | 100% | 2025-09-08 | 2026-03-31 | APPROVED | historical_confirmation
V005 | Ostmark Werkzeug GmbH | WZ-HM-EIN | TOOL-INS-CAR | 17 | 17 | 100% | 2025-09-09 | 2026-03-24 | APPROVED | historical_confirmation
V002 | Heritage Cold Heading | APH-441-OS | CHB-9472-4 | 1 | 1 | 100% |  |  | PROPOSED | current_document_context
V005 | Ostmark Werkzeug GmbH | OST-CAR-A-100 | TOOL-INS-CAR | 1 | 1 | 100% |  |  | PROPOSED | current_document_context

## UNMATCHED_LINES
PO Number | Vendor | Vendor PN | Customer PN | Description | Qty | Price | Match Method | Explanation | Source File | Issue Codes
PO-4500050001 | Apex Bar & Tube Co. |  | BAR-A286-250 | A286 bar stock, 0.250 dia, mill-cert | 1500 |  |  |  | apex_02.pdf | MISSING_PO_LINE
PO-4500060619 | Apex Bar & Tube Co. |  |  | A286 bar stock, 0.250 dia, mill-cert | 1000 |  |  |  | apex_rogue.pdf | UNKNOWN_PO

## RUN_SUMMARY
Beacon Purchasing Copilot — Run Summary
Task 1 · Open PO vs supplier acknowledgments
Metric | Value
PDFs processed | 35
Acknowledgments | 32
Revisions | 1
Invoices | 1
Scanned PDFs | 4
Cached extractions | 35
AI extractions | 0
Local/OCR extractions | 0
Open PO lines | 44
Matched lines | 40
Missing lines | 1
RED issues | 10
YELLOW issues | 4
Unknown POs | 1
Extraction failures | 0
LLM provider | local
LLM model | local-parser-v1
Offline | Y
Assumptions
Open PO unit prices are treated as USD (CSV has no currency column).
AI extracts document facts; Python computes qty/price/date discrepancies.
Invoices are not treated as formal acknowledgments.
QuickShip 'ship' dates are compared for visibility and flagged DATE_SEMANTICS_WARNING.

## FOLLOW_UPS
Vendor | Contact | PO | Subject | Suggested Email
Apex Bar & Tube Co. | orders@apexbar.com | PO-4500050001 | PO-4500050001 confirmation discrepancy | Hello, We received your document for PO-4500050001. Beacon PO PO-4500050001 line 2 (BAR-A286-250, qty 1,500 if ordered, required 2026-06-10) does not appear on the acknowledgment. Please confirm this line. Thank you. Lisa Morgan Purchasing, Beacon Fasteners
Apex Bar & Tube Co. | orders@apexbar.com | PO-4500050007 | PO-4500050007 confirmation discrepancy | Hello, We received your document for PO-4500050007. Beacon ordered 1,500 units of BAR-A286-250, while the acknowledgment confirms 1,425. Please confirm whether the remaining 75 units can be supplied by 2026-06-15. Thank you. Lisa Morgan Purchasing, Beacon Fasteners
QuickShip Industrial | orders@quickship-ind.com | PO-4500050032 | PO-4500050032 confirmation discrepancy | Hello, We received your document for PO-4500050032. We have shipment/invoice evidence for PO-4500050032 but no formal order acknowledgment. Please send a confirmation of quantity, price, and promise date. Thank you. Lisa Morgan Purchasing, Beacon Fasteners
QuickShip Industrial | orders@quickship-ind.com | PO-4500050032 | PO-4500050032 confirmation discrepancy | Hello, We received your document for PO-4500050032. We have shipment/invoice evidence for PO-4500050032 but no formal order acknowledgment. Please send a confirmation of quantity, price, and promise date. Thank you. Lisa Morgan Purchasing, Beacon Fasteners
Apex Bar & Tube Co. | orders@apexbar.com | PO-4500060619 | PO-4500060619 confirmation discrepancy | Hello, We received your document for PO-4500060619. We received an acknowledgment referencing PO-4500060619, which is not on our current open PO list. Please confirm the correct Beacon PO number. Thank you. Lisa Morgan Purchasing, Beacon Fasteners
Apex Bar & Tube Co. | orders@apexbar.com | PO-4500050002 | PO-4500050002 confirmation discrepancy | Hello, We received your document for PO-4500050002. The acknowledgment unit price differs from the PO by $0.0902/unit. Please confirm whether this is intended. Thank you. Lisa Morgan Purchasing, Beacon Fasteners
Continental Quality Heat Treat | info@continentalqht.com | PO-4500050022 | PO-4500050022 confirmation discrepancy | Hello, We received your document for PO-4500050022. The confirmed date for HT-PRECIP is 21 days after Beacon's required date of 2026-05-21. Please advise whether the required date can be recovered. Thank you. Lisa Morgan Purchasing, Beacon Fasteners
Heritage Cold Heading | sales@heritagecoldheading.com | PO-4500050012 | PO-4500050012 confirmation discrepancy | Hello, We received your document for PO-4500050012. The confirmed date for CHB-9472-4 is 14 days after Beacon's required date of 2026-06-04. Please advise whether the required date can be recovered. Thank you. Lisa Morgan Purchasing, Beacon Fasteners
Liberty Surface Finishing | service@libertysurface.com | PO-4500050016 | PO-4500050016 confirmation discrepancy | Hello, We received your document for PO-4500050016. The confirmed date for PLAT-PASV is 7 days after Beacon's required date of 2026-05-17. Please advise whether the required date can be recovered. Thank you. Lisa Morgan Purchasing, Beacon Fasteners
Liberty Surface Finishing | service@libertysurface.com | PO-4500050019 | PO-4500050019 confirmation discrepancy | Hello, We received your document for PO-4500050019. Please provide a committed quantity and promise date for PO-4500050019 line 1 (PLAT-PASV). Thank you. Lisa Morgan Purchasing, Beacon Fasteners